## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Google OAuth 2.0 Sign-In & Account Creation | Integrated Google OAuth 2.0 login interface with automatic user provisioning, JWT session storage, and global AuthContext synchronization. | 1 | chauthanhtrung/XFOODI at feature/google-oauth-2-0-sign-in-account-creation | Closed | Châu Thành Trung | 20/06/2026 | 29/06/2026 | iter1 | WP, 3_Done, Authentication | Google OAuth 2.0 Sign-In & Account Creation
Email Sign-In & JWT Refresh Token Rotation | Standard Email/Password login mechanism utilizing Access Token and Refresh Token rotation backed by Redis blacklist verification. | 2 | chauthanhtrung/XFOODI at feature/email-sign-in-jwt-refresh-token-rotation | Closed | Châu Thành Trung | 05/06/2026 | 05/06/2026 | iter1 | WP, 3_Done, Authentication | Email Sign-In & JWT Refresh Token Rotation
Multi-Tenant Subdomain Routing & Dynamic CORS | Flexible router resolving tenant subdomains ({tenant}.foodx), configuring dynamic CORS, and enforcing Prisma multi-tenant data isolation. | 3 | nguyeninhthi/XFOODI at feature/multi-tenant-subdomain-routing-dynamic-cors | Closed | Nguyễn Đình Thi | 30/06/2026 | 03/07/2026 | iter1 | WP, 3_Done, Architecture | Multi-Tenant Subdomain Routing & Dynamic CORS
Forgot Password & Email Reset Token Handler | Email password recovery service generating temporary verification tokens and UI forms for secure password reset. | 4 | nguyenuchuy/XFOODI at feature/forgot-password-email-reset-token-handler | Closed | Nguyễn Đức Huy | 04/07/2026 | 09/07/2026 | iter1 | WP, 3_Done, Authentication | Forgot Password & Email Reset Token Handler
Social Account Password Setup & Reset Page | Dedicated account management page enabling users who logged in via social providers to set up local credentials. | 5 | nguyenuchuy/XFOODI at feature/social-account-password-setup-reset-page | Closed | Nguyễn Đức Huy | 08/07/2026 | 18/07/2026 | iter1 | WP, 3_Done, Authentication | Social Account Password Setup & Reset Page
Tenant Restaurant Application Onboarding Submission | Restaurant onboarding registration portal for prospective owners to submit tenant applications, business details, and contact credentials. | 6 | chauthanhtrung/XFOODI at feature/tenant-restaurant-application-onboarding-submission | Closed | Châu Thành Trung | 27/05/2026 | 13/07/2026 | iter1 | WP, 3_Done, Tenant Onboarding | Tenant Restaurant Application Onboarding Submission
Category Management List & CRUD Form | Administrative management screen and forms to create, read, update, and delete menu categories (Appetizers, Mains, Drinks, Desserts). | 7 | nguyenuchuy/XFOODI at feature/category-management-list-crud-form | Closed | Nguyễn Đức Huy | 25/05/2026 | 28/06/2026 | iter1 | WP, 3_Done, Menu Management | Category Management List & CRUD Form
Category Display Order & Status Toggle | Interactive sorting interface allowing restaurant owners to reorder category display positions and toggle active availability. | 8 | nguyenuchuy/XFOODI at feature/category-display-order-status-toggle | Closed | Nguyễn Đức Huy | 26/05/2026 | 02/06/2026 | iter1 | WP, 3_Done, Menu Management | Category Display Order & Status Toggle
Dish & Variant Options Management | Detailed dish configuration interface for pricing, primary thumbnail images, category binding, out-of-stock toggles, and size variants. | 9 | nguyenuchuy/XFOODI at feature/dish-variant-options-management | Closed | Nguyễn Đức Huy | 14/07/2026 | 16/07/2026 | iter1 | WP, 3_Done, Menu Management | Dish & Variant Options Management
Dish Asset Upload & Image Storage Processing | Asset management service handling dish image uploads to cloud storage bucket, image compression, and file format validation. | 10 | nguyenvanlinh/XFOODI at feature/dish-asset-upload-image-storage-processing | Closed | Nguyễn Văn Linh | 05/07/2026 | 14/07/2026 | iter1 | WP, 3_Done, Asset Management | Dish Asset Upload & Image Storage Processing
Tenant Restaurant Profile & Settings Configuration | Restaurant setup panel to manage brand identity: restaurant name, logo, banner cover, contact address, hotline, and operating hours. | 11 | chauthanhtrung/XFOODI at feature/tenant-restaurant-profile-settings-configuration | Closed | Châu Thành Trung | 08/07/2026 | 10/07/2026 | iter1 | WP, 3_Done, Restaurant Management | Tenant Restaurant Profile & Settings Configuration
Multi-Tenant Landing Page & Registration Request | Platform promotional landing page highlighting XFoodi ecosystem features, subscription pricing tiers, and new tenant onboarding request form. | 12 | chauthanhtrung/XFOODI at feature/multi-tenant-landing-page-registration-request | Closed | Châu Thành Trung | 17/07/2026 | 19/07/2026 | iter1 | WP, 3_Done, Landing Page | Multi-Tenant Landing Page & Registration Request
Prisma Multi-Tenant Schema & PostgreSQL Initialization | Core infrastructure initialization with Next.js 15, Express TypeScript backend, PostgreSQL Prisma ORM database models, and Redis configuration. | 13 | chauthanhtrung/XFOODI at feature/prisma-multi-tenant-schema-postgresql-initialization | Closed | Châu Thành Trung | 01/06/2026 | 02/06/2026 | iter1 | WP, 3_Done, Architecture | Prisma Multi-Tenant Schema & PostgreSQL Initialization
Cloudflare Turnstile Bot Protection & Security Guard | Cloudflare Turnstile CAPTCHA integration protecting authentication endpoints against automated brute-force attacks and bot spamming. | 14 | nguyeninhthi/XFOODI at feature/cloudflare-turnstile-bot-protection-security-guard | Closed | Nguyễn Đình Thi | 07/06/2026 | 15/06/2026 | iter1 | WP, 3_Done, Security | Cloudflare Turnstile Bot Protection & Security Guard
QR Code Digital Menu Interface & Search | Mobile-optimized digital menu accessed via table QR code scanning, supporting category navigation, instant search, and dish detail previews. | 15 | nguyenuchuy/XFOODI at feature/qr-code-digital-menu-interface-search | Closed | Nguyễn Đức Huy | 02/06/2026 | 05/07/2026 | iter2 | WP, 3_Done, Customer Ordering | QR Code Digital Menu Interface & Search
Flavor Tag Filtering (Vegan, Spicy, Savory, Sweet) | Interactive dietary filter allowing customers to filter dishes by dietary preference and taste tags with instant UI fallback. | 16 | nguyenuchuy/XFOODI at feature/flavor-tag-filtering-vegan-spicy-savory-sweet | Closed | Nguyễn Đức Huy | 21/06/2026 | 15/07/2026 | iter2 | WP, 3_Done, Customer Ordering | Flavor Tag Filtering (Vegan, Spicy, Savory, Sweet)
Real-Time Table Cart Synchronization | Synchronized shopping cart interface for table diners, calculating total pricing, custom item instructions, and real-time multi-device cart state. | 17 | nguyeninhthi/XFOODI at feature/real-time-table-cart-synchronization | Closed | Nguyễn Đình Thi | 07/06/2026 | 19/07/2026 | iter2 | WP, 3_Done, Customer Ordering | Real-Time Table Cart Synchronization
Staff Assistance Request & Table Calling (CALL_STAFF) | Instant table assistance trigger sending real-time socket events to floor staff for table service, napkin request, or bill inquiry. | 18 | nguyeninhthi/XFOODI at feature/staff-assistance-request-table-calling-call-staff | Closed | Nguyễn Đình Thi | 04/07/2026 | 12/07/2026 | iter2 | WP, 3_Done, Customer Ordering | Staff Assistance Request & Table Calling (CALL_STAFF)
Real-Time Kitchen Display System (KDS Board) | Live order board receiving instant dining room orders via WebSockets/SignalR, displaying prep queues, cooking timers, and item fulfillment controls. | 19 | nguyeninhthi/XFOODI at feature/real-time-kitchen-display-system-kds-board | Closed | Nguyễn Đình Thi | 04/07/2026 | 11/07/2026 | iter2 | WP, 3_Done, Kitchen Operation | Real-Time Kitchen Display System (KDS Board)
Kitchen Order Item Status Update & SignalR Notifications | Interactive order state transition controls (Pending -> Cooking -> Ready) automatically pushing status alerts to floor staff devices. | 20 | nguyeninhthi/XFOODI at feature/kitchen-order-item-status-update-signalr-notifications | Closed | Nguyễn Đình Thi | 25/05/2026 | 04/06/2026 | iter2 | WP, 3_Done, Kitchen Operation | Kitchen Order Item Status Update & SignalR Notifications
Interactive 2D Table Floor Layout Builder | Floor plan manager enabling drag-and-drop 2D table layout design, capacity assignment, zone partitioning, and table status tracking. | 21 | chauthanhtrung/XFOODI at feature/interactive-2d-table-floor-layout-builder | Closed | Châu Thành Trung | 23/06/2026 | 04/07/2026 | iter2 | WP, 3_Done, Table Management | Interactive 2D Table Floor Layout Builder
Interactive 3D Table Layout Viewer (Three.js) | Advanced 3D restaurant floor visualizer built with Three.js, rendering spatial table arrangements, occupancy status, and spatial camera controls. | 22 | chauthanhtrung/XFOODI at feature/interactive-3d-table-layout-viewer-three-js | Closed | Châu Thành Trung | 04/06/2026 | 09/07/2026 | iter2 | WP, 3_Done, Table Management | Interactive 3D Table Layout Viewer (Three.js)
Online Reservation & Table Booking | Public online table reservation form allowing customers to select date, time, party size, preferred dining zone, and deposit processing. | 23 | chauthanhtrung/XFOODI at feature/online-reservation-table-booking | Closed | Châu Thành Trung | 02/06/2026 | 10/06/2026 | iter2 | WP, 3_Done, Reservation | Online Reservation & Table Booking
Automated Reservation Capacity & Auto-Assignment | Algorithm automatically matching incoming reservations to available tables based on party size, seating capacity, and time slot availability. | 24 | chauthanhtrung/XFOODI at feature/automated-reservation-capacity-auto-assignment | Closed | Châu Thành Trung | 22/06/2026 | 25/06/2026 | iter2 | WP, 3_Done, Reservation | Automated Reservation Capacity & Auto-Assignment
Reservation Confirmation Email Notification | Automated transactional email dispatch sending booking confirmation details, unique Booking Code, QR check-in voucher, and cancellation terms. | 25 | nguyenuchuy/XFOODI at feature/reservation-confirmation-email-notification | Closed | Nguyễn Đức Huy | 13/07/2026 | 18/07/2026 | iter2 | WP, 3_Done, Notification | Reservation Confirmation Email Notification
Table Deposit Rules Configuration | Policy settings panel configuring required reservation deposit fees according to table types (4-seater, 8-seater, VIP banquet) and peak hours. | 26 | chauthanhtrung/XFOODI at feature/table-deposit-rules-configuration | Closed | Châu Thành Trung | 14/06/2026 | 12/07/2026 | iter2 | WP, 3_Done, Reservation | Table Deposit Rules Configuration
Table Active Order History & Item Tracking | Real-time table order summary displaying ordered items, fulfilled dishes, pending kitchen items, subtotal calculation, and elapsed dining duration. | 27 | nguyeninhthi/XFOODI at feature/table-active-order-history-item-tracking | Closed | Nguyễn Đình Thi | 29/05/2026 | 07/06/2026 | iter2 | WP, 3_Done, Order Management | Table Active Order History & Item Tracking
Ingredient Inventory Stock & Supply Recording | Inventory management system tracking restaurant raw ingredients, stock receipts, quantity adjustments, and unit cost records. | 28 | nguyenuchuy/XFOODI at feature/ingredient-inventory-stock-supply-recording | Closed | Nguyễn Đức Huy | 20/06/2026 | 30/06/2026 | iter2 | WP, 3_Done, Inventory Management | Ingredient Inventory Stock & Supply Recording
Ingredient Category & Low Stock Alert System | Ingredient category organization interface supporting reorder threshold configuration and automated low stock alerts. | 29 | nguyenuchuy/XFOODI at feature/ingredient-category-low-stock-alert-system | Closed | Nguyễn Đức Huy | 05/07/2026 | 13/07/2026 | iter2 | WP, 3_Done, Inventory Management | Ingredient Category & Low Stock Alert System
SePay Automatic Bank Transfer Webhook Integration | Automated bank transfer payment gateway powered by SePay API webhook (POST /api/payments/sepay-webhook), parsing reference content to credit orders. | 30 | chauthanhtrung/XFOODI at feature/sepay-automatic-bank-transfer-webhook-integration | Closed | Châu Thành Trung | 23/06/2026 | 02/07/2026 | iter3 | WP, 3_Done, Payment | SePay Automatic Bank Transfer Webhook Integration
SePay Dynamic VietQR Payment Generation | Dynamic VietQR code generator (https://qr.sepay.vn/img) generating customized bank transfer QR codes with embedded order reference codes. | 31 | chauthanhtrung/XFOODI at feature/sepay-dynamic-vietqr-payment-generation | Closed | Châu Thành Trung | 11/06/2026 | 17/06/2026 | iter3 | WP, 3_Done, Payment | SePay Dynamic VietQR Payment Generation
PayOS Automated Deposit Refund & Payout Gateway | Automated reservation deposit refund system integrated with PayOS Payouts API (@payos/node payouts.create), extracting customer bank details (bankBin, accountNumber, accountName) for auto-refunding cancelled deposits. | 32 | chauthanhtrung/XFOODI at feature/payos-automated-deposit-refund-payout-gateway | Closed | Châu Thành Trung | 29/05/2026 | 04/07/2026 | iter3 | WP, 3_Done, Payment & Refund | PayOS Automated Deposit Refund & Payout Gateway
PayOS Direct Payout Testing & Retry Queue Worker | Public test payout endpoint (POST /api/wallet/payos-payout) and background retry worker (retry-refunds.ts) processing pending deposit refunds. | 33 | chauthanhtrung/XFOODI at feature/payos-direct-payout-testing-retry-queue-worker | Closed | Châu Thành Trung | 03/07/2026 | 19/07/2026 | iter3 | WP, 3_Done, Payment & Refund | PayOS Direct Payout Testing & Retry Queue Worker
Real-Time Cash Payment Settlement & Change Calculation | Cashier settlement screen allowing staff to confirm cash payments, calculate cashback change, and trigger socket PAYMENT_COMPLETED broadcasts. | 34 | chauthanhtrung/XFOODI at feature/real-time-cash-payment-settlement-change-calculation | Closed | Châu Thành Trung | 06/07/2026 | 15/07/2026 | iter3 | WP, 3_Done, Payment | Real-Time Cash Payment Settlement & Change Calculation
Cash Payment Pre-Flight Auth Token Validation Guard | Pre-flight authorization verification guard preventing 401 token expiration failures during cash payment processing. | 35 | chauthanhtrung/XFOODI at feature/cash-payment-pre-flight-auth-token-validation-guard | Closed | Châu Thành Trung | 10/07/2026 | 16/07/2026 | iter3 | WP, 3_Done, Payment | Cash Payment Pre-Flight Auth Token Validation Guard
MISA e-Invoice & Automatic VAT Invoice Generation | Electronic tax invoice module integrated with MISA e-Invoice API to issue official VAT tax invoices for completed restaurant orders. | 36 | chauthanhtrung/XFOODI at feature/misa-e-invoice-automatic-vat-invoice-generation | Closed | Châu Thành Trung | 22/06/2026 | 01/07/2026 | iter3 | WP, 3_Done, Billing & Invoicing | MISA e-Invoice & Automatic VAT Invoice Generation
Tenant Digital Wallet & Financial Balance System | Internal digital wallet management system for restaurant tenants, supporting balance top-ups, transaction logs, and payout withdrawals. | 37 | chauthanhtrung/XFOODI at feature/tenant-digital-wallet-financial-balance-system | Closed | Châu Thành Trung | 13/06/2026 | 19/06/2026 | iter3 | WP, 3_Done, Finance & Wallet | Tenant Digital Wallet & Financial Balance System
Voucher Management List & Creation Form | Promotion management panel for creating, editing, and disabling percentage or fixed-amount discount vouchers with date range validation. | 38 | nguyenuchuy/XFOODI at feature/voucher-management-list-creation-form | Closed | Nguyễn Đức Huy | 17/07/2026 | 18/07/2026 | iter3 | WP, 3_Done, Promotions | Voucher Management List & Creation Form
Voucher Application Logic & Validation Bridge | Order checkout discount engine validating voucher eligibility, minimum spend thresholds, user redemption limits, and automatic total deduction. | 39 | nguyenuchuy/XFOODI at feature/voucher-application-logic-validation-bridge | Closed | Nguyễn Đức Huy | 05/07/2026 | 07/07/2026 | iter3 | WP, 3_Done, Promotions | Voucher Application Logic & Validation Bridge
Loyalty Points Calculation & Tier Assignment | Customer reward system automatically earning points per completed order, calculating membership tiers (Bronze, Silver, Gold, Diamond), and perk unlocks. | 40 | nguyenuchuy/XFOODI at feature/loyalty-points-calculation-tier-assignment | Closed | Nguyễn Đức Huy | 27/06/2026 | 28/06/2026 | iter3 | WP, 3_Done, Promotions | Loyalty Points Calculation & Tier Assignment
Employee Management Directory & Role Granting | Staff management console for adding staff accounts, assigning system roles (Owner, Manager, Staff, Kitchen), and updating active employment status. | 41 | nguyenvanlinh/XFOODI at feature/employee-management-directory-role-granting | Closed | Nguyễn Văn Linh | 19/06/2026 | 23/06/2026 | iter3 | WP, 3_Done, Employee Management | Employee Management Directory & Role Granting
Staff Status Filtering & Work Schedule Assignment | Employee status query interface supporting multi-criteria filtering, active/inactive toggles, and work shift assignments. | 42 | nguyenvanlinh/XFOODI at feature/staff-status-filtering-work-schedule-assignment | Closed | Nguyễn Văn Linh | 19/06/2026 | 04/07/2026 | iter3 | WP, 3_Done, Employee Management | Staff Status Filtering & Work Schedule Assignment
Customer Directory & Booking History | Customer relationship directory listing registered diners, phone contacts, lifetime spend totals, reservation counts, and last visit timestamps. | 43 | nguyenuchuy/XFOODI at feature/customer-directory-booking-history | Closed | Nguyễn Đức Huy | 30/06/2026 | 15/07/2026 | iter3 | WP, 3_Done, Customer Management | Customer Directory & Booking History
Customer Data Excel Export Generator | Export utility generating formatted Excel spreadsheets containing customer contact records, spending statistics, and reservation logs. | 44 | nguyenuchuy/XFOODI at feature/customer-data-excel-export-generator | Closed | Nguyễn Đức Huy | 04/06/2026 | 03/07/2026 | iter3 | WP, 3_Done, Customer Management | Customer Data Excel Export Generator
User Profile Management & Avatar Upload | Personal account dashboard enabling users to view profile metrics, update contact information, upload profile avatars, and change passwords. | 45 | nguyenvanlinh/XFOODI at feature/user-profile-management-avatar-upload | Closed | Nguyễn Văn Linh | 01/07/2026 | 19/07/2026 | iter3 | WP, 3_Done, Account Settings | User Profile Management & Avatar Upload
Security Violation Account Blocking | Security enforcement module blocking disabled or banned user accounts across Google OAuth and Phone login authentication flows. | 46 | nguyenvanlinh/XFOODI at feature/security-violation-account-blocking | Closed | Nguyễn Văn Linh | 08/06/2026 | 23/06/2026 | iter3 | WP, 3_Done, Security | Security Violation Account Blocking
Platform System Announcements Management | Broadcast announcement system allowing super admins to publish system maintenance alerts and platform updates to all restaurant tenants. | 47 | nguyeninhthi/XFOODI at feature/platform-system-announcements-management | Closed | Nguyễn Đình Thi | 02/07/2026 | 03/07/2026 | iter3 | WP, 3_Done, Communication | Platform System Announcements Management
AI Knowledge Base Document Upload & Batching | Knowledge Base upload manager handling PDF/DOCX menu documents with sequential batching (3 files/req) to prevent 502 Proxy gateway timeouts. | 48 | nguyeninhthi/XFOODI at feature/ai-knowledge-base-document-upload-batching | Closed | Nguyễn Đình Thi | 12/07/2026 | 18/07/2026 | iter4 | WP, 3_Done, AI Assistant | AI Knowledge Base Document Upload & Batching
Vector Indexing & Admin Domain Multi-Tenant Fallback | Background AI indexing worker parsing document chunks into vector embeddings with restaurant context resolution for admin domain uploads. | 49 | nguyeninhthi/XFOODI at feature/vector-indexing-admin-domain-multi-tenant-fallback | Closed | Nguyễn Đình Thi | 14/06/2026 | 07/07/2026 | iter4 | WP, 3_Done, AI Assistant | Vector Indexing & Admin Domain Multi-Tenant Fallback
AI Assistant RAG Food Recommendation Chatbot | Interactive AI chat widget "XFoodi Assistant" providing conversational menu recommendations, ingredient answers, and dietary guidance using RAG. | 50 | nguyeninhthi/XFOODI at feature/ai-assistant-rag-food-recommendation-chatbot | Closed | Nguyễn Đình Thi | 30/06/2026 | 01/07/2026 | iter4 | WP, 3_Done, AI Assistant | AI Assistant RAG Food Recommendation Chatbot
AI Smart Cart Up-selling & Flavor Matchmaking | AI recommendation engine analyzing active cart items to suggest complementary side dishes, beverage pairings, and best-selling combos. | 51 | nguyenuchuy/XFOODI at feature/ai-smart-cart-up-selling-flavor-matchmaking | Closed | Nguyễn Đức Huy | 29/06/2026 | 02/07/2026 | iter4 | WP, 3_Done, AI Assistant | AI Smart Cart Up-selling & Flavor Matchmaking
Admin 2FA TOTP Security Control Setup | Two-Factor Authentication setup panel enabling TOTP authenticator app pairing, QR secret scanning, and mandatory 2FA enforcement. | 52 | nguyeninhthi/XFOODI at feature/admin-2fa-totp-security-control-setup | Closed | Nguyễn Đình Thi | 18/07/2026 | 19/07/2026 | iter4 | WP, 3_Done, Security | Admin 2FA TOTP Security Control Setup
2FA Backup Code Regeneration & Device Pairing | Emergency security management allowing administrators to generate emergency backup recovery codes and manage secondary authorized devices. | 53 | nguyeninhthi/XFOODI at feature/2fa-backup-code-regeneration-device-pairing | Closed | Nguyễn Đình Thi | 30/05/2026 | 03/06/2026 | iter4 | WP, 3_Done, Security | 2FA Backup Code Regeneration & Device Pairing
Platform Security Audit Log & Action Tracking | Platform-wide security audit logger recording administrative configuration changes, tenant status mutations, and security events. | 54 | nguyeninhthi/XFOODI at feature/platform-security-audit-log-action-tracking | Closed | Nguyễn Đình Thi | 04/06/2026 | 07/07/2026 | iter4 | WP, 3_Done, Security | Platform Security Audit Log & Action Tracking
Tenant Application Review & Approval Management | Super admin portal for evaluating tenant restaurant onboarding requests, inspecting business documentation, and approving schema provisioning. | 55 | chauthanhtrung/XFOODI at feature/tenant-application-review-approval-management | Closed | Châu Thành Trung | 21/06/2026 | 26/06/2026 | iter4 | WP, 3_Done, Tenant Onboarding | Tenant Application Review & Approval Management
Revenue & Sales Analytics Dashboard | Executive reporting dashboard visualizing revenue metrics across daily, weekly, and monthly intervals with interactive Recharts graphics. | 56 | chauthanhtrung/XFOODI at feature/revenue-sales-analytics-dashboard | Closed | Châu Thành Trung | 02/07/2026 | 10/07/2026 | iter4 | WP, 3_Done, Analytics | Revenue & Sales Analytics Dashboard
Top Selling Dishes & Order Metrics Chart | Analytical chart widgets displaying top performing menu items, peak ordering hours, average order values, and table occupancy rates. | 57 | chauthanhtrung/XFOODI at feature/top-selling-dishes-order-metrics-chart | Closed | Châu Thành Trung | 17/06/2026 | 26/06/2026 | iter4 | WP, 3_Done, Analytics | Top Selling Dishes & Order Metrics Chart
Community Social Feed & Restaurant Reviews | Social community page allowing diners to post restaurant reviews, share dining photos, rate culinary experiences, and interact with feedback. | 58 | nguyenvanlinh/XFOODI at feature/community-social-feed-restaurant-reviews | Closed | Nguyễn Văn Linh | 02/07/2026 | 02/07/2026 | iter4 | WP, 3_Done, Social Community | Community Social Feed & Restaurant Reviews
Social Comment Threads, Reactions & Hashtag System | Enhanced social engagement features including multi-level comment threads, post reactions, hashtag indexing, saved posts, and post sharing. | 59 | nguyenvanlinh/XFOODI at feature/social-comment-threads-reactions-hashtag-system | Closed | Nguyễn Văn Linh | 29/05/2026 | 21/06/2026 | iter4 | WP, 3_Done, Social Community | Social Comment Threads, Reactions & Hashtag System
Internationalization (i18n vi/en) Switching | Global localization framework providing seamless real-time language switching between English and Vietnamese across UI components. | 60 | nguyeninhthi/XFOODI at feature/internationalization-i18n-vi-en-switching | Closed | Nguyễn Đình Thi | 26/06/2026 | 10/07/2026 | iter4 | WP, 3_Done, User Experience | Internationalization (i18n vi/en) Switching
Global Dark / Light Theme Mode System | Theme management engine delivering smooth Dark and Light mode visual transitions using CSS variables and Ant Design tokens. | 61 | nguyeninhthi/XFOODI at feature/global-dark-light-theme-mode-system | Closed | Nguyễn Đình Thi | 16/07/2026 | 17/07/2026 | iter4 | WP, 3_Done, User Experience | Global Dark / Light Theme Mode System
Production WebSocket Fixes & TypeScript Polish | System-wide code quality assurance resolving TypeScript compilation errors, production WebSocket routing, and deployment scripts. | 62 | chauthanhtrung/XFOODI at feature/production-websocket-fixes-typescript-polish | Closed | Châu Thành Trung | 25/06/2026 | 04/07/2026 | iter4 | WP, 3_Done, DevOps & Maintenance | Production WebSocket Fixes & TypeScript Polish