## Project
Total Project Tracking
Information in columns A-E are filled during project initiation; columns F-J are filled by the end of each development iteration.
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Google OAuth 2.0 Sign-In & Account Creation | Authentication | User, Customer, Staff, Admin | Integrated Google OAuth 2.0 login interface with automatic user provisioning, JWT session storage, and global AuthContext synchronization. | Châu Thành Trung | Done | iter1 | iter4 | Upgraded dynamic redirectUri and global popup callback handler
2 | Email Sign-In & JWT Refresh Token Rotation | Authentication | User, Customer, Staff, Admin | Standard Email/Password login mechanism utilizing Access Token and Refresh Token rotation backed by Redis blacklist verification. | Châu Thành Trung | Done | iter1 | none
3 | Multi-Tenant Subdomain Routing & Dynamic CORS | Architecture | Platform Admin, Owner, Staff | Flexible router resolving tenant subdomains ({tenant}.foodx), configuring dynamic CORS, and enforcing Prisma multi-tenant data isolation. | Nguyễn Đình Thi | Done | iter1 | iter4 | Synchronized dynamic CORS matching Booca domain setup
4 | Forgot Password & Email Reset Token Handler | Authentication | User, Customer | Email password recovery service generating temporary verification tokens and UI forms for secure password reset. | Nguyễn Đức Huy | Done | iter1 | iter3 | Added direct password creation bridge for social login accounts
5 | Social Account Password Setup & Reset Page | Authentication | User, Customer | Dedicated account management page enabling users who logged in via social providers to set up local credentials. | Nguyễn Đức Huy | Done | iter1 | none
6 | Tenant Restaurant Application Onboarding Submission | Tenant Onboarding | Owner, Guest | Restaurant onboarding registration portal for prospective owners to submit tenant applications, business details, and contact credentials. | Châu Thành Trung | Done | iter1 | none
7 | Category Management List & CRUD Form | Menu Management | Owner, Admin | Administrative management screen and forms to create, read, update, and delete menu categories (Appetizers, Mains, Drinks, Desserts). | Nguyễn Đức Huy | Done | iter1 | none
8 | Category Display Order & Status Toggle | Menu Management | Owner, Admin | Interactive sorting interface allowing restaurant owners to reorder category display positions and toggle active availability. | Nguyễn Đức Huy | Done | iter1 | none
9 | Dish & Variant Options Management | Menu Management | Owner, Admin | Detailed dish configuration interface for pricing, primary thumbnail images, category binding, out-of-stock toggles, and size variants. | Nguyễn Đức Huy | Done | iter1 | iter2 | Added flavor tag filters (vegan, spicy, savory, sweet)
10 | Dish Asset Upload & Image Storage Processing | Asset Management | Owner, Admin | Asset management service handling dish image uploads to cloud storage bucket, image compression, and file format validation. | Nguyễn Văn Linh | Done | iter1 | none
11 | Tenant Restaurant Profile & Settings Configuration | Restaurant Management | Owner, Admin | Restaurant setup panel to manage brand identity: restaurant name, logo, banner cover, contact address, hotline, and operating hours. | Châu Thành Trung | Done | iter1 | iter4 | Integrated dynamic logo and banner rendering on platform landing page
12 | Multi-Tenant Landing Page & Registration Request | Landing Page | Guest, Owner | Platform promotional landing page highlighting XFoodi ecosystem features, subscription pricing tiers, and new tenant onboarding request form. | Châu Thành Trung | Done | iter1 | none
13 | Prisma Multi-Tenant Schema & PostgreSQL Initialization | Architecture | Developer | Core infrastructure initialization with Next.js 15, Express TypeScript backend, PostgreSQL Prisma ORM database models, and Redis configuration. | Châu Thành Trung | Done | iter1 | none
14 | Cloudflare Turnstile Bot Protection & Security Guard | Security | All Users | Cloudflare Turnstile CAPTCHA integration protecting authentication endpoints against automated brute-force attacks and bot spamming. | Nguyễn Đình Thi | Done | iter1 | none
15 | QR Code Digital Menu Interface & Search | Customer Ordering | Customer, Guest | Mobile-optimized digital menu accessed via table QR code scanning, supporting category navigation, instant search, and dish detail previews. | Nguyễn Đức Huy | Done | iter2 | none
16 | Flavor Tag Filtering (Vegan, Spicy, Savory, Sweet) | Customer Ordering | Customer, Guest | Interactive dietary filter allowing customers to filter dishes by dietary preference and taste tags with instant UI fallback. | Nguyễn Đức Huy | Done | iter2 | none
17 | Real-Time Table Cart Synchronization | Customer Ordering | Customer, Guest | Synchronized shopping cart interface for table diners, calculating total pricing, custom item instructions, and real-time multi-device cart state. | Nguyễn Đình Thi | Done | iter2 | iter3 | Added call-staff and assistance dispatch button
18 | Staff Assistance Request & Table Calling (CALL_STAFF) | Customer Ordering | Customer, Staff | Instant table assistance trigger sending real-time socket events to floor staff for table service, napkin request, or bill inquiry. | Nguyễn Đình Thi | Done | iter2 | iter4 | Fixed CALL_STAFF production socket broadcast routing
19 | Real-Time Kitchen Display System (KDS Board) | Kitchen Operation | Kitchen Staff, Chef | Live order board receiving instant dining room orders via WebSockets/SignalR, displaying prep queues, cooking timers, and item fulfillment controls. | Nguyễn Đình Thi | Done | iter2 | iter4 | Fixed SignalR chime alerts and added kitchen zone filtering
20 | Kitchen Order Item Status Update & SignalR Notifications | Kitchen Operation | Kitchen Staff, Staff | Interactive order state transition controls (Pending -> Cooking -> Ready) automatically pushing status alerts to floor staff devices. | Nguyễn Đình Thi | Done | iter2 | none
21 | Interactive 2D Table Floor Layout Builder | Table Management | Owner, Manager, Staff | Floor plan manager enabling drag-and-drop 2D table layout design, capacity assignment, zone partitioning, and table status tracking. | Châu Thành Trung | Done | iter2 | none
22 | Interactive 3D Table Layout Viewer (Three.js) | Table Management | Owner, Manager, Staff | Advanced 3D restaurant floor visualizer built with Three.js, rendering spatial table arrangements, occupancy status, and spatial camera controls. | Châu Thành Trung | Done | iter2 | none
23 | Online Reservation & Table Booking | Reservation | Customer, Staff, Manager | Public online table reservation form allowing customers to select date, time, party size, preferred dining zone, and deposit processing. | Châu Thành Trung | Done | iter2 | iter4 | Added self-healing reservation status logic and admin capacity bypass
24 | Automated Reservation Capacity & Auto-Assignment | Reservation | Staff, Manager | Algorithm automatically matching incoming reservations to available tables based on party size, seating capacity, and time slot availability. | Châu Thành Trung | Done | iter2 | none
25 | Reservation Confirmation Email Notification | Notification | Customer | Automated transactional email dispatch sending booking confirmation details, unique Booking Code, QR check-in voucher, and cancellation terms. | Nguyễn Đức Huy | Done | iter2 | none
26 | Table Deposit Rules Configuration | Reservation | Owner, Admin | Policy settings panel configuring required reservation deposit fees according to table types (4-seater, 8-seater, VIP banquet) and peak hours. | Châu Thành Trung | Done | iter2 | none
27 | Table Active Order History & Item Tracking | Order Management | Staff, Manager | Real-time table order summary displaying ordered items, fulfilled dishes, pending kitchen items, subtotal calculation, and elapsed dining duration. | Nguyễn Đình Thi | Done | iter2 | none
28 | Ingredient Inventory Stock & Supply Recording | Inventory Management | Owner, Manager | Inventory management system tracking restaurant raw ingredients, stock receipts, quantity adjustments, and unit cost records. | Nguyễn Đức Huy | Done | iter2 | none
29 | Ingredient Category & Low Stock Alert System | Inventory Management | Owner, Manager | Ingredient category organization interface supporting reorder threshold configuration and automated low stock alerts. | Nguyễn Đức Huy | Done | iter2 | none
30 | SePay Automatic Bank Transfer Webhook Integration | Payment | Customer, Staff | Automated bank transfer payment gateway powered by SePay API webhook (POST /api/payments/sepay-webhook), parsing reference content to credit orders. | Châu Thành Trung | Done | iter3 | none
31 | SePay Dynamic VietQR Payment Generation | Payment | Customer, Staff | Dynamic VietQR code generator (https://qr.sepay.vn/img) generating customized bank transfer QR codes with embedded order reference codes. | Châu Thành Trung | Done | iter3 | none
32 | PayOS Automated Deposit Refund & Payout Gateway | Payment & Refund | Customer, Staff, Manager | Automated reservation deposit refund system integrated with PayOS Payouts API (@payos/node payouts.create), extracting customer bank details (bankBin, accountNumber, accountName) for auto-refunding cancelled deposits. | Châu Thành Trung | Done | iter3 | iter4 | Added bankRefund metadata parser, transactional refund email alerts, and auto-refund timeout cron handler
33 | PayOS Direct Payout Testing & Retry Queue Worker | Payment & Refund | Platform Admin, Staff | Public test payout endpoint (POST /api/wallet/payos-payout) and background retry worker (retry-refunds.ts) processing pending deposit refunds. | Châu Thành Trung | Done | iter3 | none
34 | Real-Time Cash Payment Settlement & Change Calculation | Payment | Staff, Cashier | Cashier settlement screen allowing staff to confirm cash payments, calculate cashback change, and trigger socket PAYMENT_COMPLETED broadcasts. | Châu Thành Trung | Done | iter3 | iter4 | Added pre-flight auth token check and staff CASH_PAYMENT_TROUBLESHOOTING guide
35 | Cash Payment Pre-Flight Auth Token Validation Guard | Payment | Staff, Cashier | Pre-flight authorization verification guard preventing 401 token expiration failures during cash payment processing. | Châu Thành Trung | Done | iter3 | none
36 | MISA e-Invoice & Automatic VAT Invoice Generation | Billing & Invoicing | Owner, Cashier | Electronic tax invoice module integrated with MISA e-Invoice API to issue official VAT tax invoices for completed restaurant orders. | Châu Thành Trung | Done | iter3 | none
37 | Tenant Digital Wallet & Financial Balance System | Finance & Wallet | Owner, Admin | Internal digital wallet management system for restaurant tenants, supporting balance top-ups, transaction logs, and payout withdrawals. | Châu Thành Trung | Done | iter3 | none
38 | Voucher Management List & Creation Form | Promotions | Owner, Admin | Promotion management panel for creating, editing, and disabling percentage or fixed-amount discount vouchers with date range validation. | Nguyễn Đức Huy | Done | iter3 | iter4 | Completed full FE UI integration & BE API logic for production vouchers
39 | Voucher Application Logic & Validation Bridge | Promotions | Customer, Staff | Order checkout discount engine validating voucher eligibility, minimum spend thresholds, user redemption limits, and automatic total deduction. | Nguyễn Đức Huy | Done | iter3 | iter4 | Eliminated static mock data, connected real BE endpoints with data normalization bridge
40 | Loyalty Points Calculation & Tier Assignment | Promotions | Customer, Owner | Customer reward system automatically earning points per completed order, calculating membership tiers (Bronze, Silver, Gold, Diamond), and perk unlocks. | Nguyễn Đức Huy | Done | iter3 | iter4 | Connected live loyalty tier points API with safe state normalization
41 | Employee Management Directory & Role Granting | Employee Management | Owner, Manager | Staff management console for adding staff accounts, assigning system roles (Owner, Manager, Staff, Kitchen), and updating active employment status. | Nguyễn Văn Linh | Done | iter3 | none
42 | Staff Status Filtering & Work Schedule Assignment | Employee Management | Owner, Manager | Employee status query interface supporting multi-criteria filtering, active/inactive toggles, and work shift assignments. | Nguyễn Văn Linh | Done | iter3 | none | Fixed status filter query logic to support ALL status selection
43 | Customer Directory & Booking History | Customer Management | Owner, Manager | Customer relationship directory listing registered diners, phone contacts, lifetime spend totals, reservation counts, and last visit timestamps. | Nguyễn Đức Huy | Done | iter3 | none
44 | Customer Data Excel Export Generator | Customer Management | Owner, Manager | Export utility generating formatted Excel spreadsheets containing customer contact records, spending statistics, and reservation logs. | Nguyễn Đức Huy | Done | iter3 | none
45 | User Profile Management & Avatar Upload | Account Settings | User, Customer, Staff | Personal account dashboard enabling users to view profile metrics, update contact information, upload profile avatars, and change passwords. | Nguyễn Văn Linh | Done | iter3 | none
46 | Security Violation Account Blocking | Security | Platform Admin, Owner | Security enforcement module blocking disabled or banned user accounts across Google OAuth and Phone login authentication flows. | Nguyễn Văn Linh | Done | iter3 | none
47 | Platform System Announcements Management | Communication | Platform Admin, Owner | Broadcast announcement system allowing super admins to publish system maintenance alerts and platform updates to all restaurant tenants. | Nguyễn Đình Thi | Done | iter3 | none
48 | AI Knowledge Base Document Upload & Batching | AI Assistant | Owner, Manager | Knowledge Base upload manager handling PDF/DOCX menu documents with sequential batching (3 files/req) to prevent 502 Proxy gateway timeouts. | Nguyễn Đình Thi | Done | iter4 | none | Implemented sequential batch processing to eliminate 502 proxy errors
49 | Vector Indexing & Admin Domain Multi-Tenant Fallback | AI Assistant | Owner, Manager | Background AI indexing worker parsing document chunks into vector embeddings with restaurant context resolution for admin domain uploads. | Nguyễn Đình Thi | Done | iter4 | none | Added admin domain restaurant fallback for KB uploads
50 | AI Assistant RAG Food Recommendation Chatbot | AI Assistant | Customer, Guest | Interactive AI chat widget "XFoodi Assistant" providing conversational menu recommendations, ingredient answers, and dietary guidance using RAG. | Nguyễn Đình Thi | Done | iter4 | none
51 | AI Smart Cart Up-selling & Flavor Matchmaking | AI Assistant | Customer | AI recommendation engine analyzing active cart items to suggest complementary side dishes, beverage pairings, and best-selling combos. | Nguyễn Đức Huy | Done | iter4 | none | Enhanced prompt for taste tags (sweet, spicy, savory, alcohol) with fallback
52 | Admin 2FA TOTP Security Control Setup | Security | Owner, Admin | Two-Factor Authentication setup panel enabling TOTP authenticator app pairing, QR secret scanning, and mandatory 2FA enforcement. | Nguyễn Đình Thi | Done | iter4 | none
53 | 2FA Backup Code Regeneration & Device Pairing | Security | Owner, Admin | Emergency security management allowing administrators to generate emergency backup recovery codes and manage secondary authorized devices. | Nguyễn Đình Thi | Done | iter4 | none
54 | Platform Security Audit Log & Action Tracking | Security | Platform Admin | Platform-wide security audit logger recording administrative configuration changes, tenant status mutations, and security events. | Nguyễn Đình Thi | Done | iter4 | none
55 | Tenant Application Review & Approval Management | Tenant Onboarding | Platform Admin | Super admin portal for evaluating tenant restaurant onboarding requests, inspecting business documentation, and approving schema provisioning. | Châu Thành Trung | Done | iter4 | none
56 | Revenue & Sales Analytics Dashboard | Analytics | Owner, Manager | Executive reporting dashboard visualizing revenue metrics across daily, weekly, and monthly intervals with interactive Recharts graphics. | Châu Thành Trung | Done | iter4 | none
57 | Top Selling Dishes & Order Metrics Chart | Analytics | Owner, Manager | Analytical chart widgets displaying top performing menu items, peak ordering hours, average order values, and table occupancy rates. | Châu Thành Trung | Done | iter4 | none
58 | Community Social Feed & Restaurant Reviews | Social Community | Customer, Guest, Owner | Social community page allowing diners to post restaurant reviews, share dining photos, rate culinary experiences, and interact with feedback. | Nguyễn Văn Linh | Done | iter4 | none
59 | Social Comment Threads, Reactions & Hashtag System | Social Community | Customer, Guest | Enhanced social engagement features including multi-level comment threads, post reactions, hashtag indexing, saved posts, and post sharing. | Nguyễn Văn Linh | Done | iter4 | none
60 | Internationalization (i18n vi/en) Switching | User Experience | All Users | Global localization framework providing seamless real-time language switching between English and Vietnamese across UI components. | Nguyễn Đình Thi | Done | iter4 | none
61 | Global Dark / Light Theme Mode System | User Experience | All Users | Theme management engine delivering smooth Dark and Light mode visual transitions using CSS variables and Ant Design tokens. | Nguyễn Đình Thi | Done | iter4 | none
62 | Production WebSocket Fixes & TypeScript Polish | DevOps & Maintenance | Developer | System-wide code quality assurance resolving TypeScript compilation errors, production WebSocket routing, and deployment scripts. | Châu Thành Trung | Done | iter4 | none

## Iter1
Iteration Tracking - Iteration 1
Information in columns A-F must be provided as the planned scope for the iteration.
Columns B-D are copied from the sheet Product tracking list.
Columns E-I are updated/filled by the end of the iteration.
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Google OAuth 2.0 Sign-In & Account Creation | Authentication | Integrated Google OAuth 2.0 login interface with automatic user provisioning, JWT session storage, and global AuthContext synchronization. | Châu Thành Trung | Done | SRS-1.1 | SDS-3.1 | Commit: feat(auth): Google OAuth 2.0 implementation
2 | Email Sign-In & JWT Refresh Token Rotation | Authentication | Standard Email/Password login mechanism utilizing Access Token and Refresh Token rotation backed by Redis blacklist verification. | Châu Thành Trung | Done | SRS-1.2 | SDS-3.2 | Commit: feat(auth): JWT authentication & Redis token rotation
3 | Multi-Tenant Subdomain Routing & Dynamic CORS | Architecture | Flexible router resolving tenant subdomains ({tenant}.foodx), configuring dynamic CORS, and enforcing Prisma multi-tenant data isolation. | Nguyễn Đình Thi | Done | SRS-5.1 | SDS-3.14 | Commit: feat(core): configure dynamic base domain for multi-tenant
4 | Forgot Password & Email Reset Token Handler | Authentication | Email password recovery service generating temporary verification tokens and UI forms for secure password reset. | Nguyễn Đức Huy | Done | SRS-1.5 | SDS-3.5 | Commit: feat(email): password reset email template & dynamic URL
5 | Social Account Password Setup & Reset Page | Authentication | Dedicated account management page enabling users who logged in via social providers to set up local credentials. | Nguyễn Đức Huy | Done | SRS-1.4 | SDS-3.7 | Commit: feat(change-password): dynamic password setting without current password
6 | Tenant Restaurant Application Onboarding Submission | Tenant Onboarding | Restaurant onboarding registration portal for prospective owners to submit tenant applications, business details, and contact credentials. | Châu Thành Trung | Done | SRS-5.1 | SDS-3.11 | Commit: feat(tenant): restaurant application submission form
7 | Category Management List & CRUD Form | Menu Management | Administrative management screen and forms to create, read, update, and delete menu categories (Appetizers, Mains, Drinks, Desserts). | Nguyễn Đức Huy | Done | SRS-2.9 | SDS-3.59 | Commit: feat(fe): complete category management UI
8 | Category Display Order & Status Toggle | Menu Management | Interactive sorting interface allowing restaurant owners to reorder category display positions and toggle active availability. | Nguyễn Đức Huy | Done | SRS-2.9 | SDS-3.60 | Commit: feat(categories): order sorting & status toggle
9 | Dish & Variant Options Management | Menu Management | Detailed dish configuration interface for pricing, primary thumbnail images, category binding, out-of-stock toggles, and size variants. | Nguyễn Đức Huy | Done | SRS-2.3 | SDS-3.62 | Commit: feat(fe): complete dish management UI & variants
10 | Dish Asset Upload & Image Storage Processing | Asset Management | Asset management service handling dish image uploads to cloud storage bucket, image compression, and file format validation. | Nguyễn Văn Linh | Done | SRS-2.3 | SDS-3.63 | Commit: feat(storage): image upload service
11 | Tenant Restaurant Profile & Settings Configuration | Restaurant Management | Restaurant setup panel to manage brand identity: restaurant name, logo, banner cover, contact address, hotline, and operating hours. | Châu Thành Trung | Done | SRS-5.3 | SDS-3.12 | Commit: feat(ui): display registered restaurant logo and images
12 | Multi-Tenant Landing Page & Registration Request | Landing Page | Platform promotional landing page highlighting XFoodi ecosystem features, subscription pricing tiers, and new tenant onboarding request form. | Châu Thành Trung | Done | SRS-5.2 | SDS-3.17 | Commit: feat(landing): multi-tenant landing page
13 | Prisma Multi-Tenant Schema & PostgreSQL Initialization | Architecture | Core infrastructure initialization with Next.js 15, Express TypeScript backend, PostgreSQL Prisma ORM database models, and Redis configuration. | Châu Thành Trung | Done | SRS-1.1 | SDS-3.14 | Commit: feat(db): prisma schema setup & multi-tenant models
14 | Cloudflare Turnstile Bot Protection & Security Guard | Security | Cloudflare Turnstile CAPTCHA integration protecting authentication endpoints against automated brute-force attacks and bot spamming. | Nguyễn Đình Thi | Done | SRS-7.2 | SDS-3.10 | Commit: feat(security): Cloudflare Turnstile integration
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in columns A-F must be provided as the planned scope for the iteration.
Columns B-D are copied from the sheet Product tracking list.
Columns E-I are updated/filled by the end of the iteration.
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Dish & Variant Options Management | Menu Management | Detailed dish configuration interface for pricing, primary thumbnail images, category binding, out-of-stock toggles, and size variants. | Nguyễn Đức Huy | Updated | SRS-2.3 | SDS-3.62 | Commit: feat(fe): complete dish management UI & variants
2 | QR Code Digital Menu Interface & Search | Customer Ordering | Mobile-optimized digital menu accessed via table QR code scanning, supporting category navigation, instant search, and dish detail previews. | Nguyễn Đức Huy | Done | SRS-6.3 | SDS-3.31 | Commit: feat(menu): QR code digital menu interface
3 | Flavor Tag Filtering (Vegan, Spicy, Savory, Sweet) | Customer Ordering | Interactive dietary filter allowing customers to filter dishes by dietary preference and taste tags with instant UI fallback. | Nguyễn Đức Huy | Done | SRS-2.3 | SDS-3.18 | Commit: feat(menu): flavor tag filter & dietary preferences
4 | Real-Time Table Cart Synchronization | Customer Ordering | Synchronized shopping cart interface for table diners, calculating total pricing, custom item instructions, and real-time multi-device cart state. | Nguyễn Đình Thi | Done | SRS-6.3 | SDS-3.31 | Commit: feat(cart): real-time cart sync
5 | Staff Assistance Request & Table Calling (CALL_STAFF) | Customer Ordering | Instant table assistance trigger sending real-time socket events to floor staff for table service, napkin request, or bill inquiry. | Nguyễn Đình Thi | Done | SRS-3.3 | SDS-3.32 | Commit: fix(socket): fix CALL_STAFF not working on production
6 | Real-Time Kitchen Display System (KDS Board) | Kitchen Operation | Live order board receiving instant dining room orders via WebSockets/SignalR, displaying prep queues, cooking timers, and item fulfillment controls. | Nguyễn Đình Thi | Done | SRS-3.2 | SDS-3.45 | Commit: feat(kds): live kitchen display board
7 | Kitchen Order Item Status Update & SignalR Notifications | Kitchen Operation | Interactive order state transition controls (Pending -> Cooking -> Ready) automatically pushing status alerts to floor staff devices. | Nguyễn Đình Thi | Done | SRS-2.13 | SDS-3.47 | Commit: feat(kds): order item status update & push notification
8 | Interactive 2D Table Floor Layout Builder | Table Management | Floor plan manager enabling drag-and-drop 2D table layout design, capacity assignment, zone partitioning, and table status tracking. | Châu Thành Trung | Done | SRS-2.5 | SDS-3.68 | Commit: feat(table): 2D floor plan layout builder
9 | Interactive 3D Table Layout Viewer (Three.js) | Table Management | Advanced 3D restaurant floor visualizer built with Three.js, rendering spatial table arrangements, occupancy status, and spatial camera controls. | Châu Thành Trung | Done | SRS-2.5 | SDS-3.69 | Commit: feat(map): interactive 3D table floor layout
10 | Online Reservation & Table Booking | Reservation | Public online table reservation form allowing customers to select date, time, party size, preferred dining zone, and deposit processing. | Châu Thành Trung | Done | SRS-6.2 | SDS-3.25 | Commit: feat(reservation): online table booking system
11 | Automated Reservation Capacity & Auto-Assignment | Reservation | Algorithm automatically matching incoming reservations to available tables based on party size, seating capacity, and time slot availability. | Châu Thành Trung | Done | SRS-2.6 | SDS-3.28 | Commit: feat(reservation): capacity check auto-assignment
12 | Reservation Confirmation Email Notification | Notification | Automated transactional email dispatch sending booking confirmation details, unique Booking Code, QR check-in voucher, and cancellation terms. | Nguyễn Đức Huy | Done | SRS-2.6 | SDS-3.26 | Commit: feat(email): automated reservation confirmation email
13 | Table Deposit Rules Configuration | Reservation | Policy settings panel configuring required reservation deposit fees according to table types (4-seater, 8-seater, VIP banquet) and peak hours. | Châu Thành Trung | Done | SRS-6.1 | SDS-3.30 | Commit: feat(reservation): configurable table deposit rules
14 | Table Active Order History & Item Tracking | Order Management | Real-time table order summary displaying ordered items, fulfilled dishes, pending kitchen items, subtotal calculation, and elapsed dining duration. | Nguyễn Đình Thi | Done | SRS-3.2 | SDS-3.40 | Commit: feat(orders): table order history tracking
15 | Ingredient Inventory Stock & Supply Recording | Inventory Management | Inventory management system tracking restaurant raw ingredients, stock receipts, quantity adjustments, and unit cost records. | Nguyễn Đức Huy | Done | SRS-2.7 | SDS-3.70 | Commit: feat(inventory): raw ingredient stock & supply management
16 | Ingredient Category & Low Stock Alert System | Inventory Management | Ingredient category organization interface supporting reorder threshold configuration and automated low stock alerts. | Nguyễn Đức Huy | Done | SRS-2.7 | SDS-3.72 | Commit: feat(inventory): ingredient category & low stock threshold alerts
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in columns A-F must be provided as the planned scope for the iteration.
Columns B-D are copied from the sheet Product tracking list.
Columns E-I are updated/filled by the end of the iteration.
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Forgot Password & Email Reset Token Handler | Authentication | Email password recovery service generating temporary verification tokens and UI forms for secure password reset. | Nguyễn Đức Huy | Updated | SRS-1.5 | SDS-3.5 | Commit: feat(email): password reset email template & dynamic URL
2 | Real-Time Table Cart Synchronization | Customer Ordering | Synchronized shopping cart interface for table diners, calculating total pricing, custom item instructions, and real-time multi-device cart state. | Nguyễn Đình Thi | Updated | SRS-6.3 | SDS-3.31 | Commit: feat(cart): real-time cart sync
3 | SePay Automatic Bank Transfer Webhook Integration | Payment | Automated bank transfer payment gateway powered by SePay API webhook (POST /api/payments/sepay-webhook), parsing reference content to credit orders. | Châu Thành Trung | Done | SRS-3.4 | SDS-3.34 | Commit: feat(payment): SePay webhook payment gateway integration
4 | SePay Dynamic VietQR Payment Generation | Payment | Dynamic VietQR code generator (https://qr.sepay.vn/img) generating customized bank transfer QR codes with embedded order reference codes. | Châu Thành Trung | Done | SRS-3.4 | SDS-3.34 | Commit: feat(payment): SePay dynamic VietQR payment generation
5 | PayOS Automated Deposit Refund & Payout Gateway | Payment & Refund | Automated reservation deposit refund system integrated with PayOS Payouts API (@payos/node payouts.create), extracting customer bank details (bankBin, accountNumber, accountName) for auto-refunding cancelled deposits. | Châu Thành Trung | Done | SRS-3.4 | SDS-3.54 | Commit: feat(payos): automated reservation deposit refund payout gateway
6 | PayOS Direct Payout Testing & Retry Queue Worker | Payment & Refund | Public test payout endpoint (POST /api/wallet/payos-payout) and background retry worker (retry-refunds.ts) processing pending deposit refunds. | Châu Thành Trung | Done | SRS-3.4 | SDS-3.54 | Commit: feat(wallet): direct PayOS payout testing & retry queue worker
7 | Real-Time Cash Payment Settlement & Change Calculation | Payment | Cashier settlement screen allowing staff to confirm cash payments, calculate cashback change, and trigger socket PAYMENT_COMPLETED broadcasts. | Châu Thành Trung | Done | SRS-3.4 | SDS-3.52 | Commit: fix(live-orders): Add pre-flight auth check for cash payment
8 | Cash Payment Pre-Flight Auth Token Validation Guard | Payment | Pre-flight authorization verification guard preventing 401 token expiration failures during cash payment processing. | Châu Thành Trung | Done | SRS-3.4 | SDS-3.52 | Commit: docs(payments): Verify cash payment socket emission working
9 | MISA e-Invoice & Automatic VAT Invoice Generation | Billing & Invoicing | Electronic tax invoice module integrated with MISA e-Invoice API to issue official VAT tax invoices for completed restaurant orders. | Châu Thành Trung | Done | SRS-3.4 | SDS-3.53 | Commit: feat(invoice): MISA e-Invoice VAT invoice integration
10 | Tenant Digital Wallet & Financial Balance System | Finance & Wallet | Internal digital wallet management system for restaurant tenants, supporting balance top-ups, transaction logs, and payout withdrawals. | Châu Thành Trung | Done | SRS-3.4 | SDS-3.52 | Commit: feat(wallet): tenant digital wallet balance & transactions
11 | Voucher Management List & Creation Form | Promotions | Promotion management panel for creating, editing, and disabling percentage or fixed-amount discount vouchers with date range validation. | Nguyễn Đức Huy | Done | SRS-2.12 | SDS-3.73 | Commit: feat(fe-voucher): complete voucher management UI & logic
12 | Voucher Application Logic & Validation Bridge | Promotions | Order checkout discount engine validating voucher eligibility, minimum spend thresholds, user redemption limits, and automatic total deduction. | Nguyễn Đức Huy | Done | SRS-2.12 | SDS-3.35 | Commit: feat(be-voucher): voucher redemption & application bridge
13 | Loyalty Points Calculation & Tier Assignment | Promotions | Customer reward system automatically earning points per completed order, calculating membership tiers (Bronze, Silver, Gold, Diamond), and perk unlocks. | Nguyễn Đức Huy | Done | SRS-2.12 | SDS-3.76 | Commit: feat(be-voucher): loyalty points calculation
14 | Employee Management Directory & Role Granting | Employee Management | Staff management console for adding staff accounts, assigning system roles (Owner, Manager, Staff, Kitchen), and updating active employment status. | Nguyễn Văn Linh | Done | SRS-2.2 | SDS-3.55 | Commit: feat(employee): staff management & role assignment
15 | Staff Status Filtering & Work Schedule Assignment | Employee Management | Employee status query interface supporting multi-criteria filtering, active/inactive toggles, and work shift assignments. | Nguyễn Văn Linh | Done | SRS-2.2 | SDS-3.58 | Commit: fix(employee): resolve status filter query logic
16 | Customer Directory & Booking History | Customer Management | Customer relationship directory listing registered diners, phone contacts, lifetime spend totals, reservation counts, and last visit timestamps. | Nguyễn Đức Huy | Done | SRS-2.4 | SDS-3.80 | Commit: feat(restaurant): customer management directory
17 | Customer Data Excel Export Generator | Customer Management | Export utility generating formatted Excel spreadsheets containing customer contact records, spending statistics, and reservation logs. | Nguyễn Đức Huy | Done | SRS-2.4 | SDS-3.80 | Commit: feat(restaurant): customer list excel export generator
18 | User Profile Management & Avatar Upload | Account Settings | Personal account dashboard enabling users to view profile metrics, update contact information, upload profile avatars, and change passwords. | Nguyễn Văn Linh | Done | SRS-1.6 | SDS-3.9 | Commit: feat(profile): user profile page with avatar upload
19 | Security Violation Account Blocking | Security | Security enforcement module blocking disabled or banned user accounts across Google OAuth and Phone login authentication flows. | Nguyễn Văn Linh | Done | SRS-1.1 | SDS-3.10 | Commit: security(auth): block disabled users in Google and Phone login
20 | Platform System Announcements Management | Communication | Broadcast announcement system allowing super admins to publish system maintenance alerts and platform updates to all restaurant tenants. | Nguyễn Đình Thi | Done | SRS-2.1 | SDS-3.44 | Commit: feat(announcements): system broadcast announcement manager
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in columns A-F must be provided as the planned scope for the iteration.
Columns B-D are copied from the sheet Product tracking list.
Columns E-I are updated/filled by the end of the iteration.
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Google OAuth 2.0 Sign-In & Account Creation | Authentication | Integrated Google OAuth 2.0 login interface with automatic user provisioning, JWT session storage, and global AuthContext synchronization. | Châu Thành Trung | Updated | SRS-1.1 | SDS-3.1 | Commit: feat(auth): Google OAuth 2.0 implementation
2 | Multi-Tenant Subdomain Routing & Dynamic CORS | Architecture | Flexible router resolving tenant subdomains ({tenant}.foodx), configuring dynamic CORS, and enforcing Prisma multi-tenant data isolation. | Nguyễn Đình Thi | Updated | SRS-5.1 | SDS-3.14 | Commit: feat(core): configure dynamic base domain for multi-tenant
3 | Tenant Restaurant Profile & Settings Configuration | Restaurant Management | Restaurant setup panel to manage brand identity: restaurant name, logo, banner cover, contact address, hotline, and operating hours. | Châu Thành Trung | Updated | SRS-5.3 | SDS-3.12 | Commit: feat(ui): display registered restaurant logo and images
4 | Staff Assistance Request & Table Calling (CALL_STAFF) | Customer Ordering | Instant table assistance trigger sending real-time socket events to floor staff for table service, napkin request, or bill inquiry. | Nguyễn Đình Thi | Updated | SRS-3.3 | SDS-3.32 | Commit: fix(socket): fix CALL_STAFF not working on production
5 | Real-Time Kitchen Display System (KDS Board) | Kitchen Operation | Live order board receiving instant dining room orders via WebSockets/SignalR, displaying prep queues, cooking timers, and item fulfillment controls. | Nguyễn Đình Thi | Updated | SRS-3.2 | SDS-3.45 | Commit: feat(kds): live kitchen display board
6 | Online Reservation & Table Booking | Reservation | Public online table reservation form allowing customers to select date, time, party size, preferred dining zone, and deposit processing. | Châu Thành Trung | Updated | SRS-6.2 | SDS-3.25 | Commit: feat(reservation): online table booking system
7 | PayOS Automated Deposit Refund & Payout Gateway | Payment & Refund | Automated reservation deposit refund system integrated with PayOS Payouts API (@payos/node payouts.create), extracting customer bank details (bankBin, accountNumber, accountName) for auto-refunding cancelled deposits. | Châu Thành Trung | Updated | SRS-3.4 | SDS-3.54 | Commit: feat(payos): automated reservation deposit refund payout gateway
8 | Real-Time Cash Payment Settlement & Change Calculation | Payment | Cashier settlement screen allowing staff to confirm cash payments, calculate cashback change, and trigger socket PAYMENT_COMPLETED broadcasts. | Châu Thành Trung | Updated | SRS-3.4 | SDS-3.52 | Commit: fix(live-orders): Add pre-flight auth check for cash payment
9 | Voucher Management List & Creation Form | Promotions | Promotion management panel for creating, editing, and disabling percentage or fixed-amount discount vouchers with date range validation. | Nguyễn Đức Huy | Updated | SRS-2.12 | SDS-3.73 | Commit: feat(fe-voucher): complete voucher management UI & logic
10 | Voucher Application Logic & Validation Bridge | Promotions | Order checkout discount engine validating voucher eligibility, minimum spend thresholds, user redemption limits, and automatic total deduction. | Nguyễn Đức Huy | Updated | SRS-2.12 | SDS-3.35 | Commit: feat(be-voucher): voucher redemption & application bridge
11 | Loyalty Points Calculation & Tier Assignment | Promotions | Customer reward system automatically earning points per completed order, calculating membership tiers (Bronze, Silver, Gold, Diamond), and perk unlocks. | Nguyễn Đức Huy | Updated | SRS-2.12 | SDS-3.76 | Commit: feat(be-voucher): loyalty points calculation
12 | AI Knowledge Base Document Upload & Batching | AI Assistant | Knowledge Base upload manager handling PDF/DOCX menu documents with sequential batching (3 files/req) to prevent 502 Proxy gateway timeouts. | Nguyễn Đình Thi | Done | SRS-4.2 | SDS-3.78 | Commit: feat(ai): RAG knowledge base batch uploading & indexing
13 | Vector Indexing & Admin Domain Multi-Tenant Fallback | AI Assistant | Background AI indexing worker parsing document chunks into vector embeddings with restaurant context resolution for admin domain uploads. | Nguyễn Đình Thi | Done | SRS-4.2 | SDS-3.78 | Commit: fix: POST /api/ai/kb/upload 400 Bad Request admin fallback
14 | AI Assistant RAG Food Recommendation Chatbot | AI Assistant | Interactive AI chat widget "XFoodi Assistant" providing conversational menu recommendations, ingredient answers, and dietary guidance using RAG. | Nguyễn Đình Thi | Done | SRS-4.3 | SDS-3.33 | Commit: feat(recommendation): enhance AI prompt for flavor matchmaking
15 | AI Smart Cart Up-selling & Flavor Matchmaking | AI Assistant | AI recommendation engine analyzing active cart items to suggest complementary side dishes, beverage pairings, and best-selling combos. | Nguyễn Đức Huy | Done | SRS-4.1 | SDS-3.33 | Commit: feat(ai): AI Menu Recommendations (frequently-bought + cart)
16 | Admin 2FA TOTP Security Control Setup | Security | Two-Factor Authentication setup panel enabling TOTP authenticator app pairing, QR secret scanning, and mandatory 2FA enforcement. | Nguyễn Đình Thi | Done | SRS-1.1 | SDS-3.10 | Commit: feat: implement enhanced admin 2FA security controls
17 | 2FA Backup Code Regeneration & Device Pairing | Security | Emergency security management allowing administrators to generate emergency backup recovery codes and manage secondary authorized devices. | Nguyễn Đình Thi | Done | SRS-1.1 | SDS-3.10 | Commit: feat: backup codes regeneration and secondary device setup
18 | Platform Security Audit Log & Action Tracking | Security | Platform-wide security audit logger recording administrative configuration changes, tenant status mutations, and security events. | Nguyễn Đình Thi | Done | SRS-2.1 | SDS-3.79 | Commit: feat(audit): system audit logging & security tracking
19 | Tenant Application Review & Approval Management | Tenant Onboarding | Super admin portal for evaluating tenant restaurant onboarding requests, inspecting business documentation, and approving schema provisioning. | Châu Thành Trung | Done | SRS-5.1 | SDS-3.13 | Commit: feat(admin): tenant application review & approval workflow
20 | Revenue & Sales Analytics Dashboard | Analytics | Executive reporting dashboard visualizing revenue metrics across daily, weekly, and monthly intervals with interactive Recharts graphics. | Châu Thành Trung | Done | SRS-2.1 | SDS-3.79 | Commit: feat(dashboard): revenue analytics & sales charts
21 | Top Selling Dishes & Order Metrics Chart | Analytics | Analytical chart widgets displaying top performing menu items, peak ordering hours, average order values, and table occupancy rates. | Châu Thành Trung | Done | SRS-2.1 | SDS-3.79 | Commit: feat(dashboard): top dishes & order volume metrics
22 | Community Social Feed & Restaurant Reviews | Social Community | Social community page allowing diners to post restaurant reviews, share dining photos, rate culinary experiences, and interact with feedback. | Nguyễn Văn Linh | Done | SRS-2.4 | SDS-3.36 | Commit: feat(social): add community feed page and API integration
23 | Social Comment Threads, Reactions & Hashtag System | Social Community | Enhanced social engagement features including multi-level comment threads, post reactions, hashtag indexing, saved posts, and post sharing. | Nguyễn Văn Linh | Done | SRS-2.4 | SDS-3.36 | Commit: feat(social): comment threads, reactions & hashtag search
24 | Internationalization (i18n vi/en) Switching | User Experience | Global localization framework providing seamless real-time language switching between English and Vietnamese across UI components. | Nguyễn Đình Thi | Done | SRS-7.1 | SDS-3.12 | Commit: feat(i18n): multi-language support (vi/en)
25 | Global Dark / Light Theme Mode System | User Experience | Theme management engine delivering smooth Dark and Light mode visual transitions using CSS variables and Ant Design tokens. | Nguyễn Đình Thi | Done | SRS-7.1 | SDS-3.12 | Commit: feat(ui): dark & light theme mode system
26 | Production WebSocket Fixes & TypeScript Polish | DevOps & Maintenance | System-wide code quality assurance resolving TypeScript compilation errors, production WebSocket routing, and deployment scripts. | Châu Thành Trung | Done | SRS-7.2 | SDS-3.14 | Commit: fix(ts): resolve TypeScript compilation & production build
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document